## Sheet1
| SPRINT BACKLOG: 1 | GROUP NO: | Mon L29
Task No. | Task Description: | Assigned to: | To be completed by: | Date Uploaded to file exchange area | Reassigned to, on date: | To be completed by: | Date uploaded to file exchange area | Notes:
1a | Read through scenario and produce initial stakeholder list | Alan | 2020-04-17 | 2020-03-14
1b | Do some research on functional requirements and how to write them | Bogdan | 2020-04-17 | 2020-03-15
1c | Submit draft functional requirements for stakeholders a and b | Samir | 2020-04-17 | 2020-03-16
1d | Submit draft functional requirements for stakeholders a and b | Emad | 2020-04-17 | 2020-03-17
… | …. |  | 2020-04-17 | 2020-03-18
2 | Submit draft functional requirements for stakeholders c and d | Emad | 2020-04-17 | 2020-03-19
3 | Submit draft functional requirements for stakeholders e and f | Bogdan | 2020-04-17 | 2020-03-20
4 | Produce draft ERD for publication area | Alan | 2020-04-17 | 2020-03-21
.. | ……...etc |  | 2020-04-17 | 2020-03-22
6 | Produce draft ERD for project admin area | Samir | 2020-04-17 | 2020-03-23
7 | Data Dictionary | Alan | 2020-04-17 | 2020-03-24
8 | Query/Form Design | Samir | 2020-04-17 | 2020-03-25
9 | Normalisation | Emad | 2020-04-17 | 2020-03-26
10 | Update ER Diagram | Alan | 2020-04-17 | 2020-03-27
11 | Some changes and addition in database documentation | Emad | 2020-04-17 | 2020-03-27
12 | erd_V5 | Alan | 2020-04-17 | 2020-04-11
13 | Crating specification table from the chosen topic from ERD | Bogdan | 2020-04-17 | 2020-04-11
14 | Crating specification table from the chosen topic from ERD | Samir | 2020-04-17 | 2020-04-12
15 | Some updates on entity specification table | Bogdan | 2020-04-17 | 2020-04-12
16 | Requirements and stakeholders update | Bogdan | 2020-04-17 | 2020-04-12
17 | Entity specification form from researcher conference | Emad | 2020-04-17 | 2020-04-12
18 | Entity spec_budget,project,future project | Alan | 2020-04-17 | 2020-04-12